## Dashboard
Habio launch QA checklist — dashboard
How to use this workbook
- Each tab (Customer App, Professional App, Backend & Shared Logic) lists every screen or piece of logic built so far, grouped the way the app actually flows.
- Set the Status column as you confirm what state something is really in: Not Built, Built - Not Tested, Deployed - Not Tested, or Deployed and Confirmed.
- Set the Tested? column as you physically walk through each screen on a device: Not Started, In Progress, Pass, or Fail.
- Priority flags what should block launch (Launch Blocker) vs what can slip (High / Medium / Low). Adjust freely - the starting values are a judgment call based on the engineering log.
- Use Notes / issues found to record anything broken, half-working, or needing a follow-up decision from you.
- The counts below update automatically from all three sheets as you edit the Status column.
Status counts across all three sheets
Status | Customer App | Professional App | Backend & Shared Logic | Total
Not Built | 8 | 10 | 0 | 18
Built - Not Tested | 9 | 2 | 4 | 15
Deployed - Not Tested | 1 | 15 | 3 | 19
Deployed and Confirmed | 18 | 11 | 10 | 39
Total items | 36 | 38 | 17 | 91
Launch blocker count by sheet
Sheet | Launch Blockers (any status) | Launch Blockers still Not Built or Not Tested
Customer App | 9 | 9
Professional App | 5 | 5
Backend & Shared Logic | 7 | 2
Last reviewed 2026-09-08 by Claude -- statuses cross-checked against this week's engineering session (App Check fix, request-data-completeness fix, availability re-match addition) and the project's master to-do / engineering log. Adjust anything that doesn't match what you're actually seeing.

## Customer App
Habio launch QA checklist — Customer App
Section | Screen / Feature | What it does | Status | Tested? | Priority | Notes / issues found
Entry
| Splash screen | Standard timing splash, cityscape decoration, logo. | Deployed and Confirmed | Pass | Low
| Onboarding carousel (3 pages) | Handshake / describe-problem / completed-service illustrated pages, shown once before login. | Deployed and Confirmed | Not Started | Medium
| Login / OTP screen | Phone entry + OTP verify. Logo enlarged 70x70 to 100x100. | Deployed and Confirmed | Pass | Medium | OTP login itself has been used continuously throughout testing -- every other confirmed flow (bidding, chat, cancellation) depends on being logged in, so this is clearly working. The specific 100x100 logo resize hasn't been separately visually confirmed.
Home screen
| Quick Services section | 2-card row for Cleaning + Helper Services with Fixed price badge, routes into tier-based flow. | Built - Not Tested | Not Started | Launch Blocker
| Browse Categories grid | All 15 non-quick categories, filters out the 2 Quick Services categories. | Built - Not Tested | Not Started | Launch Blocker
| Trending Services | Currently inactive placeholder, no real logic or Firestore wiring yet. | Not Built | Not Started | Medium
| Emergency / Night Services | Currently inactive placeholder, scope not yet defined. | Not Built | Not Started | Medium
| Frequently Used section | Existing, already-live widget, untouched by recent work. | Deployed and Confirmed | Not Started | Low
Standard request flow (15 bidding categories)
| Category -> Subcategory screen | Subcategory picker; 4 categories (Metal Fab, Glass, Fabric, Decoration) newly added, needs a fresh build to appear. | Built - Not Tested | Not Started | Launch Blocker
| Add request details | Free-text / structured details for the job. | Deployed and Confirmed | Not Started | Low
| Confirm location screen | Address capture and pin confirmation. | Deployed and Confirmed | Not Started | Low
| Date / time screen | 24 specific 1-hour slots plus Anytime, replacing old Morning/Afternoon/Evening buckets. Shared by every category. | Built - Not Tested | Not Started | Launch Blocker
| Review & Submit screen | Shows 'Request Quotes' CTA for bidding requests. | Deployed and Confirmed | Not Started | Medium | 2026-09-08: fixed a bug where category/subcategory/address/date/time-slot were silently dropped when the request was written to Firestore (a gap between the ServiceRequest and ServiceRequestModel classes) -- the professional's opportunity card was showing incomplete details as a result. Fix committed to request_service.dart/request_repository.dart/finding_professionals_screen.dart; needs a fresh end-to-end request to confirm the professional now sees full details.
| Finding Professionals (bidding copy) | Transition screen with quotation-oriented copy. | Deployed and Confirmed | Not Started | Low
| Bid list screen | Real Firestore bid stream, compare bids, accept a bid. | Deployed and Confirmed | Not Started | High
Quick Services request flow (Cleaning + Helper Services)
| Fixed-price request screen (tier picker) | 3 tiers per subcategory across all 32 subcategories, 96 placeholder prices need review. | Built - Not Tested | Not Started | Launch Blocker
| Address screen (reused) | Same AddressScreen as bidding flow, unmodified. | Deployed and Confirmed | Not Started | Low
| Review & Submit (fixed-price copy) | Shows 'Submit Request' CTA instead of Request Quotes. | Deployed and Confirmed | Not Started | Medium
| Finding Professionals (fixed-price copy) | Conditional copy: 'price already set, waiting for acceptance'. | Built - Not Tested | Not Started | Medium
| Fixed Price Waiting screen | Raise-price bottom sheet, 45-second 'taking longer than usual' banner. | Built - Not Tested | Not Started | Launch Blocker
Order lifecycle (shared)
| Order Status screen | Confirmed / active / completed states, professional contact card. | Deployed and Confirmed | Not Started | High
| Cancellation flow (payment-gated redesign) | cancelOrder only records intent; order stays active until payCancellationFee actually clears it. | Deployed - Not Tested | Not Started | Launch Blocker | Backend functions (cancelOrder, payCancellationFee) were redeployed 2026-09-08 alongside the App Check fix, so the full loop can now actually be tested end-to-end -- that walkthrough hasn't happened yet.
| Cancellation fee payment sheet (mocked) | Ppay 150 rupees mock sheet, already confirmed working by Harsh once. | Deployed and Confirmed | Pass | Medium
| Rate & Review screen | One review per completed order, immutable once submitted. | Deployed and Confirmed | Not Started | Low
Bookings tab
| Ongoing / Completed / Cancelled tabs | Three-stage bookings list. | Deployed and Confirmed | Not Started | Medium
| Upcoming card routing fix | Fixed-price requests now route to Waiting screen instead of the bid list. | Built - Not Tested | Not Started | High
| Pay button swap on pending fee | Card button switches Cancel -> Pay 150 rupees while a fee is pending. | Deployed and Confirmed | Not Started | Low
Profile / support
| Support chat (customer to admin) | Confirmed end to end, admin replies via standalone console. | Deployed and Confirmed | Pass | Low
| Public professional profile view | Ratings, completed jobs count, review history, portfolio photos. | Deployed and Confirmed | Not Started | Low
Not yet built (customer side)
| Live GPS tracking | En-route / on-the-way map view of the assigned professional. | Not Built | Not Started | High
| OTP-to-start-job (customer side) | Customer receives and shares a one-time code with the professional on arrival. | Not Built | Not Started | High
| Real Razorpay payment UI | Live gateway checkout, replacing the fully mocked payment flow. | Not Built | Not Started | Launch Blocker
| Minimum floor price reference on bid UI | Soft 'near market rate' reference across all categories, not just Quick Services. | Not Built | Not Started | Medium
| Multi-day estimated completion display | Shown only for subcategories flagged multi-day-eligible. | Not Built | Not Started | Medium
| Tiered cancellation fee logic | 5% of order cost for multi-day-eligible jobs, vs flat 150 rupees otherwise. | Not Built | Not Started | Medium
Fixes & additions since last QA pass (2026-09-08)
| Request data completeness fix (category/address/date/time-slot) | Customer-side write path (ServiceRequestModel/RequestService/RequestRepository) was silently dropping these fields before they reached Firestore, even though the professional app already knew how to read them. | Built - Not Tested | Not Started | Launch Blocker | Root cause of the 'request card still does not show details' bug reported this week. Fixed and committed to the customer app 2026-09-08. Needs: submit a fresh test request end-to-end and confirm the professional's opportunity card shows category, address, date and time slot.

## Professional App
Habio launch QA checklist — Professional App
Section | Screen / Feature | What it does | Status | Tested? | Priority | Notes / issues found
Entry
| Splash screen | Cityscape decoration matching customer app, 5-second timing. | Deployed and Confirmed | Pass | Low
| Post-splash intro carousel | Overhauled 2026-09-04 to use real mascot artwork (price-setting / matched-jobs / earnings) replacing the earlier code-drawn character. | Deployed - Not Tested | Not Started | Medium | Shipped as part of the professional app's real release build (~2026-09-06/07, the ~74MB release APK); not separately walked through on-device.
| Login / OTP screen | Phone entry + OTP verify, separate file from the customer app's OTP screen. | Deployed and Confirmed | Pass | Low
Onboarding wizard
| Name / about / experience step | Basic profile fields. | Deployed and Confirmed | Not Started | Low
| Category + subcategory picker | Mirrored taxonomy; needs rebuild to show the 4 newly added categories. | Deployed - Not Tested | Not Started | Launch Blocker | Shipped in the professional app's real release build -- the rebuild this needed has happened. Not yet visually confirmed that all 4 new categories (Metal Fabrication, Glass Work, Fabric & Tailoring, Decoration & Events) actually appear.
| Business vs Individual choice | Business path requires GST number plus certificate upload; raises active-order cap to 5 and adds an Employee Assigned field on bids. | Deployed - Not Tested | Not Started | Medium | Shipped in the same release build as the category picker rebuild above.
| Service area + location + radius step | Geolocator-based capture, configurable service radius. | Deployed and Confirmed | Not Started | Low
| Optional referral-code entry | New field on VerificationScreen, resolved against referral_codes collection. | Built - Not Tested | Not Started | Medium | Client-side field is shipped in the release build, but resolving a code depends on firestore.rules for the new referral_codes collection -- that rules deploy (firebase deploy --only firestore:rules) hasn't been confirmed run yet, so entering a code may currently fail with a permission error. Test only after that deploy.
| Verification screen (document upload) | PAN / Aadhaar / bank statement / photo upload. isVerified is still an auto-true placeholder. | Deployed and Confirmed | Not Started | Medium
Professional home
| Welcome header with real name | Fixed from a hardcoded 'Welcome to Habio' string. | Deployed - Not Tested | Not Started | Medium | Shipped in the release build; not separately confirmed the header shows the real name rather than the old hardcoded string.
| Service location chip | Now defaults to the professional's real registered area instead of a hardcoded city. | Deployed - Not Tested | Not Started | Medium | Shipped in the release build; not separately confirmed.
| Bell + Requests tab badge | Counts outstanding SENT opportunities directly, not the notifications list. | Deployed and Confirmed | Not Started | Low
| Referral popup (once per app open) | Closeable via top-right X, links to the shared Refer & Earn screen. | Deployed - Not Tested | Not Started | Medium | Shipped in the release build; not separately confirmed the popup only fires once per app open.
Opportunities
| Standard bid opportunity + submission | Accept/Ignore card leads into full bid composition (price, materials, warranty etc). | Deployed and Confirmed | Pass | High | 2026-09-08: the customer-side data-completeness fix (category/address/date/time-slot no longer dropped on submit -- see Customer App sheet) means bid opportunity cards should now show full request details; not yet re-confirmed live since that fix.
| Fixed-price opportunity card | Accept or Ignore only, shows tier label and below-floor warning. | Deployed - Not Tested | Not Started | Launch Blocker | Shipped in the release build. Also benefits from the 2026-09-08 customer-side data-completeness fix for the tier label / full details. Not yet walked through live.
| First-to-accept-wins race guard | Transaction throws already-exists for the second professional to accept. | Deployed - Not Tested | Not Started | Launch Blocker | The Cloud Function transaction logic this depends on was redeployed 2026-09-08 alongside the App Check fix (a full firebase deploy --only functions was run). The actual race-condition test (two professionals accepting at once) still hasn't been attempted.
Job execution
| Job Details screen (real) | Streams the real order, Start Job / Complete Job call real Cloud Functions. | Deployed and Confirmed | Pass | High
| accepted_job_screen.dart (orphaned mock) | Dead code, never navigated to. Decide: leave or delete. | Not Built | Not Started | Low
| Withdraw from Job (150 rupee fee) | Auto-deducted from wallet, order re-matched to other professionals. | Deployed and Confirmed | Not Started | High
| Job completion photos | 1 to 3 mandatory photos, enforced server-side, feeds public portfolio. | Deployed and Confirmed | Not Started | Low
| In-job pickup escalation (Automobile / Appliances) | Condition photos + OTP at pickup and delivery, 5-state sub-status chain. Rare exception path. | Not Built | Not Started | Medium
Wallet / earnings
| Earnings screen | Wired to real wallet_ledger; shows completed jobs, withdrawal-fee entries, referral-commission entries. | Deployed - Not Tested | Not Started | High | Client is in the release build; the wallet-crediting Cloud Functions it depends on (completeJob, referral commission) were redeployed 2026-09-08. Not yet walked through live.
| Instant payout for orders >= 5000 rupees + WhatsApp PDF | Explicitly deferred trust-building feature. | Not Built | Not Started | Low
Profile tab
| My Skills | Reads/writes real subcategoryIds against the real taxonomy, replacing an unrelated hardcoded list. | Deployed - Not Tested | Not Started | Launch Blocker | Shipped in the release build; not separately confirmed on-device.
| Personal Details | Real name/about/email prefilled, phone shown read-only. | Deployed - Not Tested | Not Started | Medium | Shipped in the release build; not separately confirmed on-device.
| Verification Status (new, read-only) | Shows real document/verified status without forcing re-upload. | Deployed - Not Tested | Not Started | Medium | Shipped in the release build; not separately confirmed on-device.
| Service Area (rebuilt) | Normal Profile-subscreen chrome, real location/radius prefill, use-current-location action. | Deployed - Not Tested | Not Started | Launch Blocker | Shipped in the release build; not separately confirmed on-device.
| Profile completeness percentage | Now computed from 5 real checks instead of a hardcoded 80 percent; weighting is a judgment call worth reviewing. | Deployed - Not Tested | Not Started | Low | Shipped in the release build; not separately confirmed on-device.
| Refer & Earn screen | Code display/share, reward explanation, stats, referred-professionals list. | Built - Not Tested | Not Started | Medium | Same firestore.rules dependency as the referral-code entry above (row 12) -- the referred-professionals list / stats query may fail until that rules deploy runs.
| My Reviews screen | Average rating, completed jobs, full review list. | Deployed and Confirmed | Not Started | Low
Conduct / training (onboarding gate)
| Tier 1: written conduct policy + agree step | Single source-of-truth policy text with an explicit acknowledgment step. | Not Built | Not Started | High
| Tier 2: conduct video + completion tracking | 10-15 minute video narrating Tier 1 policy; quiz vs checkbox gating undecided. | Not Built | Not Started | Medium
| Tier 3: skill training (Helper Services + Beauty) | Needs a qualified external content source; timing (pre vs post funding) undecided. | Not Built | Not Started | Low
Not yet built (professional side)
| OTP-to-start-job (professional side) | Professional enters the customer-shared code to unlock Start Job. | Not Built | Not Started | High
| Admin panel | Full UI replacing raw Firebase Console for operations. | Not Built | Not Started | Medium
| Real document verification flow | Replacing the temporary isVerified auto-true stand-in. | Not Built | Not Started | High
| GPS en-route broadcast | Professional's live location feed for the customer's tracking view. | Not Built | Not Started | High
Fixes & additions since last QA pass (2026-09-08)
| 'No new requests' empty state (Requests tab) | Shows an icon + 'No new requests' + explanatory text when there are no active opportunities. | Deployed - Not Tested | Not Started | Medium | Harsh reported a blank white screen instead of this message after the recent Firestore data reset. Code reviewed line-by-line 2026-09-08 (professional_opportunities_screen.dart) -- the empty-state widget and its StreamBuilder branch are both correctly written, so this is very likely a stale installed build or a hot-reload glitch, not a code bug. Needs: flutter clean + a fresh release build/reinstall (or a full stop+restart if running via flutter run), then re-check.

## Backend & Shared Logic
Habio launch QA checklist — Backend & Shared Logic
Section | Screen / Feature | What it does | Status | Tested? | Priority | Notes / issues found
Matching & bidding
| matchProfessionalsToRequest engine | Core eligible-professional search + opportunity fan-out. Untouched through every recent change. | Deployed and Confirmed | Pass | Launch Blocker
| Bid pipeline (bid_service.dart, opportunity docs) | Bids stored as fields on the opportunity doc, not a separate collection. | Deployed and Confirmed | Pass | High
Order lifecycle Cloud Functions
| acceptBid / acceptFixedPriceOpportunity | Creates the order doc, closes other opportunities, increments activeOrderCount. | Deployed and Confirmed | Pass | Launch Blocker | Confirmed working 2026-09-08 -- this was the function behind the 'Accept job' Unauthenticated bug; fixed by disabling App Check enforcement (see row below) and confirmed working afterward.
| startJob / completeJob | Status transitions, mandatory completion photos, commission + referral crediting. | Deployed and Confirmed | Pass | Launch Blocker
| cancelOrder / payCancellationFee (redesigned) | Payment-gated split: order stays active until the fee is actually paid. | Deployed - Not Tested | Not Started | Launch Blocker | Deployed via the 2026-09-08 firebase deploy --only functions run (done alongside the App Check fix) -- the earlier 'needs a deploy' blocker is cleared. Not yet live-tested.
| professionalWithdrawOrder | Atomic withdrawal + re-match to other eligible professionals. | Deployed and Confirmed | Not Started | High
| raiseFixedPriceOrder | Customer-initiated price raise, re-broadcasts via the existing matching function. | Deployed and Confirmed | Pass | High | This was the function behind the 'Raise price' Unauthenticated bug reported 2026-09-08 -- fixed by disabling App Check enforcement and confirmed working afterward ('Now it works').
| Referral commission crediting (in completeJob) | 1 percent of job fees excluding materials, credited to referrer, gated on 1-year window. | Deployed - Not Tested | Not Started | Medium | Deployed via the same 2026-09-08 functions deploy. Still needs firebase deploy --only firestore:rules for the referral_codes rules before a real end-to-end referral test (two accounts) is possible.
Notifications & support
| createNotification on lifecycle events | New opportunity, bid accepted/submitted, job started/completed, payment, review, cancellation. | Deployed and Confirmed | Pass | Medium
| Support chat + admin console | Standalone HTML admin tool, confirmed working end to end. | Deployed and Confirmed | Pass | Low
Security & infra
| Firestore rules (referral_codes, collection-group, admin gate) | Latest additions not yet deployed. | Built - Not Tested | Not Started | Launch Blocker | Needs firebase deploy --only firestore:rules. Still not deployed as of 2026-09-08 -- this is now the one blocker on the referral program actually working end-to-end (see the two rows above).
| App Check enforcement (9 callable functions) | Code shipped with enforceAppCheck true on every callable function. | Deployed and Confirmed | Pass | Launch Blocker | Reversed 2026-09-08: enforceAppCheck was deliberately flipped from true to false on all 9 callable functions, because Play Integrity only validates a Play-Store-installed app and both apps are still sideloaded with no Play Console account yet -- with it left on, every one of these calls was failing before it even reached the function body, surfacing as a bare 'Unauthenticated' error. This change was deployed and confirmed to fix Accept Job / Raise Price. Re-enable once the company's Play Console account is registered (needs a D-U-N-S number) and the app is installed via its Internal Testing track -- this condition is saved to memory, not due yet.
| Android code shrinking + obfuscation (R8/ProGuard) | Release build minify + resource shrink turned on both apps. | Deployed - Not Tested | In Progress | High | Needs one real release build + full smoke test. The professional app's real release build (~2026-09-06/07) uses this build config (R8/ProGuard minify+shrink is the standard release setting). Core flows built on it (accept bid, raise price) have worked fine post-build, so nothing critical has broken so far -- but no dedicated full smoke test has been done yet.
| Dart obfuscation (build_release.bat) | Obfuscated app bundle build script; symbols folder must be stored privately per release. | Built - Not Tested | Not Started | Medium | The professional release APK built this week used a plain flutter build apk --release, not build_release.bat -- so Dart obfuscation specifically was NOT applied to that build. Still needs a build via the obfuscation script to actually test this item.
| Maps API key out of plaintext manifest | Moved to gitignored secrets.properties per app. | Built - Not Tested | Not Started | Medium | Still needs SHA-1 restriction on the key in Google Cloud Console.
Data state
| Firestore fully wiped (2026-09-04 reset) | No registered professionals, requests, orders, reviews, or wallet balances currently exist. | Deployed and Confirmed | Not Started | Launch Blocker | Every test above needs fresh signups first. A further reset appears to have been requested again in early September (the same firebase firestore:delete --recursive --force instructions as the 2026-09-04 wipe, to be run by Harsh himself) -- not explicitly confirmed done in chat, but the professional app showing zero active opportunities during this week's testing is consistent with it having been carried out. Worth a quick confirmation.
Additions since last QA pass (2026-09-08)
| onProfessionalAvailabilityChanged (re-match on availability ON) | Previously, matching only ran once at request creation -- a professional toggled off when a request came in would never see it, even after toggling back on. New Cloud Function fires when a professional's isAvailable flips to true and fans out fresh opportunities for every still-open request they're eligible for (same capability/category/radius rules as the original matching engine), skipping anything they've already been shown or that's already been awarded. | Built - Not Tested | Not Started | High | Added 2026-09-08 per Harsh's report. Needs firebase deploy --only functions, then a live test: toggle a professional off, submit a matching request as a customer, toggle the professional back on, confirm the request appears on their Requests tab within a few seconds.